## Tabelle1
User Story | Tasks | Original Estimation | Current Estimation | Effort | Remain | Responsible
Unregister sign | Create Unregister button (with select list) | 2h | 2h |  | 2h
| Remove tablet correctly from DB | 2h | 2h |  | 2h
| Add alerts in case of errors | 2h | 2h |  | 2h
Register sign | Create Room Selection Page | 3h | 3h |  | 3h
| Get correct information from DB via server + display right | 4h | 4h |  | 4h
| Handle errors | 2h | 2h |  | 2h
Define event | Create "Define Event"-Page: 1. choose which tablets for the event | 4h | 4h |  | 4h | Felix
| Create "Define Event"-Page: 2. be able to enter data and choose view for each tablet separately | 7h | 7h |  | 7h | Felix
| Interaction with server/DB regarding saving data correctly | 4h | 4h |  | 4h | Belmin
| Add to timeline | 4h | 4h |  | 4h | Sara
Delete from timeline | Create "Delete event from timeline" page (with select list) | 1h | 1h |  | 1h
| Remove event correctly from DB and stop displaying | 2h | 2h |  | 2h
| Handle errors | 1h | 1h |  | 1h
Update event in timeline | Create "Update event from timeline" page | 3h | 3h |  | 3h
| Save edited info correctly into the DB | 2h | 2h |  | 2h
| Handle errors | 2h | 2h |  | 2h
Show free computer rooms | Create computer rooms overview | 6h | 6h |  | 6h
| Get correct information from DB via server + display right | 3h | 3h |  | 3h
| Handle errors | 2h | 2h |  | 2h
Show timeline overview for admin page | Create timeline overview | 6h | 6h |  | 6h
| Get correct information from DB via server + display right | 3h | 3h |  | 3h